## Cover
Request for Proposal (RFP) to Appoint Electricity Importers
Submission: Technical Section
Contents:
A2.2.2 - List of Surveys
A3.1.1 - List of Required Permits
A3.3.4 - Design Phase Risks
A4.1.2 - Construction Phase Risks
A5.2.1 - Asset Failure Causation
A6.2.1 - Financing Track Record
A6.2.2 - FID/FC Requirements
Participant: | Insert Name
Date of Submission: | Insert Date

## A2.2.2-List of Surveys
Request for Proposal (RFP) to Appoint Electricity Importers
Submission: Technical Section
A2.2.2 - List of Surveys
| Participant: | Insert Name
ID | Survey | Description/Objective | Onshore/Offshore | Territory (Country) | Relevant Asset | Project Phase | Survey Type | Comments
Example | Protected species environmental survey (desktop) | Initial desktop study to identify the possible presence of protected species and define target location for physical investigation | Onshore | Country name | Onshore Cable | Design | Desktop study | Desktop study has been completed to inform route corridor definition. Physical investigations (see items X and Y in this register) are currently being procured and planned for H2 2022.
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## A3.1.1-List of Req. Permits
Request for Proposal (RFP) to Appoint Electricity Importers
Submission: Technical Section
A3.1.1 - List of Required Permits
| Participant: | Insert Name
ID | Permit | Description | Onshore/Offshore | Territory (Country) | Relevant Asset | Key Information Requirements | Criticality | Permit deliberation timeframe | Comments/narrative
Example | Local Authority Planning Permission | Planning permit required for local planning authority X to authorise the construction of the asset | Onshore | Country name | Converter Station | -Environmental Impact Assessment -Outline design -Traffic model …. | High | 9-12 months | The volume of requirements and the extended deliberation timeframe make this permit a clear part of the project's design phase critical path. Engagement with local authority to date has been positive and there is clear support for the scheme. Currently, outline design is in progress and environmental surveys are expected to start in XXX.
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## A3.3.4-Design Phase Risk
Request for Proposal (RFP) to Appoint Electricity Importers
Submission: Technical Section
A3.3.4 - Design Phase Risks
| Participant: | Insert Name
ID | Risk Title | Location | Country | Cause | Consequence | Criticality | Best Case Scenario Description | Most Likely Scenario Description | Worst Case Scenario Description | Management Plan
Example | Unforeseen protected fauna | Converter station site | Country name | Ecology surveys identify presence of unforeseen protected specie on site | Cost and time associated with further ecology surveys and environmental mitigations | Medium | Protected specie limited to a minor portion of the site. Minor environmental mitigations required with no delay to the design phase schedule. | Protected specie limited to a minor portion of the site. Minor environmental mitigations required with no delay to the design phase schedule. | Protected specie found across the whole site. Additional surveys and significant environmental mitigations required delaying the design phase schedule by 12 months. | 1. Early desktop studies (desktop stuides have been now completed) 2. Early planning of environmental surveys (environmental surveys have been planned and are being procured) 3. Conservative (extensive) scope of physical ecology surveys
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## A4.1.2-Contruction Phase Risk
Request for Proposal (RFP) to Appoint Electricity Importers
Submission: Technical Section
A4.1.2 - Construction Phase Risks
| Participant: | Insert Name
ID | Risk Title | Location | Country | Cause | Consequence | Criticality | Best Case Scenario Description | Most Likely Scenario Description | Worst Case Scenario Description | Management Plan
Example | Unforeseen unfavourable seabed conditions | Offshore cable route | Country name | Seabed conditions differ from conditions identified by surveys | Cost and time associated with re-burial and rock-dumping activities | High | Unfavourable conditions restricted to a small section of the route and addressed with a change in installation tool. No delay to construction schedule. | Unfavourable conditions restricted to a moderate section of the route and addressed with changes in installation tools, re-burial and rock dumping. No delay to the construction phase schedule. | Unfavourable conditions on a significant section of the cable route and addressed with changes in installation tools, re-burial and rock dumping. Delay to the construction phase schedule of XX months. | 1. Burial risk assessment to be… 2. Contractual risk allocation to be…
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## A5.2.1-Asset Failure Causation
Request for Proposal (RFP) to Appoint Electricity Importers
Submission: Technical Section
A5.2.1 - Asset Failure Causation
| Participant: | Insert Name
ID | Asset | Failure Risk | Description | Management Plan
Example | Subsea cable | Third party damage (e.g. anchor) | Third party vessel anchor hits and damages the cable | 1. Burial depth… 2. Expected operational arrangements
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## A6.2.1-Financing Track Record
Request for Proposal (RFP) to Appoint Electricity Importers
Submission: Technical Section
A6.2.1 - Financing Track Record
| Participant: | Insert Name
ID | Example | Description | Completion Date | Value of Financing Secured | Relevance | Team
Example | Project X | Brief description of the project, including the purpose and type of financing that was secured. | 2019-06-01 | Value in original currency | Brief statement on why the experience is relevant to the Participant's import project | State who from the Participant's organisation(s) was involved.
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## A6.2.2-FID FC Requirements
Request for Proposal (RFP) to Appoint Electricity Importers
Submission: Technical Section
A6.2.2 - FID/FC Requirements
| Participant: | Insert Name
ID | FID/FC Requirements | Description | Expected Date of Requirement Completion | Current Status | Next Steps
Example | Local Authority Planning Permission | Requirement to start construction activities at XXX site | 2024-06-01 | -Ongoing positive engagement with authority -XXX activities currently in development | -Completion of XXX activity -Public consultation…
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Dropdowns (hidden)
Criticality | Onshore/Offshore | Timeframe | Survey Type | Project Phase
High | Onshore | 0-3 months | Desktop study | Design
Medium | Offshore | 3-6 months | Physical investigation | Construction
Low | All | 6-9 months
9-12 months
12-18 months
18+ months